# CU1 — Social Media Marketing
Strategic Campaign Plan

Ref: TVET-CU1-SMM-003

Organisation: TVET Lipis — Fokus Kiara Sdn Bhd

Prepared by: Zuriel Seong Ming Ee — Head of Sales & Digital Marketing

Campaign: 2026 Full-Time Intake Recruitment

Campaign Window: 90 days (January – March 2025)

Work Activities Covered: WA3 (Plan Social Media Campaign), WA4 (Manage Campaign)

## 1. Strategic Purpose

This Strategic Campaign Plan defines the management framework for TVET Lipis's 2026 Full-Time Intake social media recruitment campaign. It establishes SMART objectives, resource requirements, campaign architecture, and KPI thresholds for management review. The plan operates at the planning and coordination level — operational execution details are managed within the Implementation Summary (TVET-CU1-SMM-004).

## 2. SMART Objectives

Based on historical performance benchmark of RM 4.61 per lead (Meta Ads account act_494800392480239):

| Objective Element | Definition |
| --- | --- |
| Specific | Generate 500 qualified leads for the 2026 full-time intake via Facebook and Instagram |
| Measurable | Tracked via Meta Pixel, Lead Forms, and CRM (WhatsApp lead log) |
| Achievable | Historical CTR 1.33%–1.70%; target CPL ≤ RM 5.00; previous campaigns achieved RM 4.61/lead |
| Relevant | Directly supports TVET Lipis's enrollment target of 60 students per intake cycle |
| Time-bound | 90-day window: January – March 2025. Weekly KPI review with management escalation if off-track |

## 3. Campaign Architecture

| Campaign Tier | Objective | Audience | Content Type | Budget % |
| --- | --- | --- | --- | --- |
| Tier 1 — Awareness (Top of Funnel) | Reach & educate parents | Cold: Parents aged 25–44, Pahang + neighbouring states, education interest | Video ("Day in the Life"), Carousel ("Why TVET?") | 30% — RM 750 |
| Tier 2 — Consideration (Mid Funnel) | Drive link clicks + enquiries | Warm: Engaged with Tier 1 content | Long-form copywriting, testimonials, program explainers | 40% — RM 1,000 |
| Tier 3 — Conversion (Bottom Funnel) | Lead form submissions | Hot: Retarget video viewers + profile visitors | Lead form ads, urgency "Limited Seats" posts | 30% — RM 750 |
| Total | — | — | — | RM 2,500 |

## 4. Resource Allocation

| Resource Category | Requirement | Description |
| --- | --- | --- |
| Manpower | Zuriel Seong Ming Ee (Media Buyer + Copywriter) | Campaign strategy, ad management, copywriting |
|  | Designer (part-time) | Visual asset creation (images, carousels, video thumbnails) |
|  | Admin support | Lead follow-up, CRM data entry, WhatsApp responses |
| Budget | RM 2,500 – RM 3,000 (90 days) | Based on RM 5.00 target CPL × 500–600 leads |
| Tools | Meta Business Suite | Campaign management, reporting, audience builder |
|  | Canva / Adobe CC | Visual asset creation |
|  | Respond.io | Lead communication automation + CRM integration |
|  | Google Analytics 4 | Cross-channel attribution tracking |

## 5. KPIs & Performance Thresholds

| KPI | Target | Escalation Trigger |
| --- | --- | --- |
| Total Leads (90 days) | 500 leads | < 250 leads at Day 45 → campaign review |
| Cost Per Lead (CPL) | ≤ RM 5.00 | > RM 7.00 CPL → pause + optimize |
| CTR (all) | ≥ 1.30% | < 1.00% → creative refresh required |
| Facebook CTR | ≥ 1.50% | < 1.20% → ad copy revision |
| Lead Form Completion Rate | ≥ 60% | < 40% → simplify form fields |
| Weekly Lead Volume | 55+ leads/week | < 30/week at Week 3 → budget reallocation |

## 6. Management Focus — Budget & Task Delegation

| Item | Budget (90 days) | Notes |
| --- | --- | --- |
| Facebook Ads spend | RM 1,625 | 65% of total campaign budget |
| Instagram Ads spend | RM 875 | 35% of total campaign budget |
| Creative production | RM 450 | 3 video + 6 carousel assets |
| Tools (Respond.io, Canva) | RM 165 | Monthly × 3 months |
| Total campaign budget | RM 3,115 | Subject to management approval |

| Task | Responsible | Frequency |
| --- | --- | --- |
| Campaign strategy & brief | Zuriel Seong Ming Ee | Pre-launch |
| Weekly performance report to mgmt | Zuriel → Lee Bee Chuan | Weekly |
| Budget reallocation decisions | Lee Bee Chuan (approval required) | As needed |
| Creative approval (new assets) | Lee Bee Chuan | Per creative batch |
| 90-day campaign review | Zuriel (full report) | End of campaign |

## Approval Section

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Zuriel Seong Ming Ee — Head of Sales & Digital Marketing | ___________________ | ___________ |
| Reviewed by | [PPT Supervisor / Assessor — Pending] | ___________________ | ___________ |
| Approved by | Lee Bee Chuan Managing Director, Fokus Kiara Sdn Bhd | ___________________ | ___________ |