# CU1 — Social Media Marketing
Task Implementation Summary Report

Ref: TVET-CU1-SMM-004

Organisation: TVET Lipis — Fokus Kiara Sdn Bhd

Prepared by: Zuriel Seong Ming Ee — Head of Sales & Digital Marketing

Report Period: January 2025 (Campaign Setup Phase)

Campaign: 2026 Full-Time Intake — "Full Time Parents 2026"

Work Activities Covered: WA4 (Implement Campaign), WA5 (Monitor & Coordinate)

## 1. Strategic Purpose

This Implementation Summary Report serves as the management oversight document for the campaign setup and early execution phase of the "Full Time Parents 2026" campaign. It consolidates task delegation status, completion tracking, and escalation flags to ensure management has a real-time view of campaign readiness. Decisions on resource reallocation and deadline adjustments are made at this review level.

## 2. Task Delegation & Status

| Task ID | Task Description | Assigned To | Status | Deadline | Notes |
| --- | --- | --- | --- | --- | --- |
| T01 | Audience Research & Persona Finalization | Zuriel Seong Ming Ee | ✅ Completed | Week 1 | Data from Meta Ads (act_494800392480239) — 90-day analysis |
| T02 | Creative Asset Production (Images/Videos) | Designer | 🔄 In Progress | Week 2 | Video: "Fara PAKK VS PRA"; Carousel: program comparison |
| T03 | Ad Copywriting (Malay & English) | Zuriel Seong Ming Ee | ✅ Completed | Week 2 | "PAKK Copywriting Lama" proven format; 3 variants ready |
| T04 | Meta Pixel & Conversion API Setup | Technical Lead | ✅ Completed | Week 1 | Pixel verified; Lead Form conversion event configured |
| T05 | Campaign Launch & Initial Testing | Zuriel (Media Buyer) | ⏳ Pending | Week 3 | Awaiting creative final batch — expected Week 2 completion |
| T06 | CRM Integration (Respond.io) | Zuriel Seong Ming Ee | ✅ Completed | Week 2 | Lead form → Respond.io → WhatsApp auto-reply configured |
| T07 | Budget Allocation Approval | Lee Bee Chuan (approval) | ⏳ Pending | Week 1 | RM 3,115 campaign budget submitted for sign-off |
| T08 | Meta Business Suite Account Verification | Zuriel Seong Ming Ee | ✅ Completed | Week 1 | FB Page + IG Business linked; 2FA enabled |

## 3. Work Progress Monitoring Checklist

| Milestone | Status | Completion Date |
| --- | --- | --- |
| Social Media Channel Verification (FB/IG) | ✅ Done | Week 1 |
| Budget Allocation Approval | ⏳ Pending | Awaiting Lee Bee Chuan sign-off |
| Content Calendar Finalization | ✅ Done | Week 1 |
| Creative Assets Uploaded to Media Library | 🔄 60% | Week 2 (in progress) |
| Lead Form Integration with CRM | ✅ Done | Week 2 |
| Campaign Launch | ⏳ Pending | Week 3 (pending budget approval) |

Overall Campaign Setup Completion: 60% (as of end of Week 2)

## 4. Risk & Escalation Log

| Risk | Impact | Status | Action |
| --- | --- | --- | --- |
| Creative asset delay (T02) | Medium — may delay Week 3 launch | Active | Designer briefed; deadline extended by 2 days |
| Budget approval pending (T07) | High — campaign cannot launch without | Active | Escalated to Lee Bee Chuan — awaiting sign-off |
| Lead form drop-off rate | Medium — affects CPL target | Monitoring | A/B test 2 form variants post-launch |
| Audience saturation (long campaign) | Low — mitigated by audience refresh | Planned | Lookalike audiences prepared for Week 5+ |

## 5. Management Focus — Coordination Summary

All tasks falling behind by more than 48 hours are escalated to management via WhatsApp daily update. Critical path: T07 (Budget Approval) → T05 (Campaign Launch). Campaign launch date is contingent on budget approval from Lee Bee Chuan.

| Weekly Review | Meeting Format | Participants |
| --- | --- | --- |
| Week 1 (Setup) | Briefing + checklist review | Zuriel + Lee Bee Chuan |
| Week 2 (Creative) | Creative review session | Zuriel + Designer + Lee Bee Chuan |
| Week 3 (Launch) | Launch readiness sign-off | Zuriel + Lee Bee Chuan |
| Weekly ongoing | Performance WhatsApp update | Zuriel → Lee Bee Chuan |

## Approval Section

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Zuriel Seong Ming Ee — Head of Sales & Digital Marketing | ___________________ | ___________ |
| Reviewed by | [PPT Supervisor / Assessor — Pending] | ___________________ | ___________ |
| Approved by | Lee Bee Chuan Managing Director, Fokus Kiara Sdn Bhd | ___________________ | ___________ |