# CU1 — Social Media Marketing
Paid Advertisement Campaign Proposal

Ref: TVET-CU1-SMM-005

Organisation: TVET Lipis — Fokus Kiara Sdn Bhd

Prepared by: Zuriel Seong Ming Ee — Head of Sales & Digital Marketing

Campaign: 2026 Recruitment Drive (Paid Tier)

Platform: Meta Ads — Facebook + Instagram

Work Activities Covered: WA5 (Plan Paid Social Media), WA6 (Implement Paid Campaign)

## 1. Strategic Purpose

This Paid Advertisement Proposal defines the budget, targeting parameters, and A/B testing strategy for TVET Lipis's paid social media component of the 2026 Recruitment Drive. Paid campaigns amplify organic reach and accelerate lead generation during the critical 8-week pre-intake window. All proposed spend and targeting criteria are derived from the historical performance of the "Full Time Parents 2026" campaign and are presented for management budget approval.

## 2. Historical Performance Baseline

| Metric | Historical Benchmark (act_494800392480239) | Target for 2026 Drive |
| --- | --- | --- |
| Cost Per Lead (CPL) | RM 4.61 | ≤ RM 5.00 |
| CTR (all) | 1.33% | ≥ 1.50% |
| Top Segment | Female, 35–44 years | Maintain + expand 25–34 female |
| Top Placement | Facebook News Feed (Mobile) | Facebook News Feed + IG Reels |
| Top Content | "PAKK Copywriting Lama" | Copywriting + Video A/B test |

## 3. Budget & Target Matching

| Campaign Objective | Target Metric | Volume Target | Est. Cost / Result | Required Budget (MYR) |
| --- | --- | --- | --- | --- |
| Lead Generation | Leads (Meta Lead Form) | 200 | RM 5.00 | RM 1,000 |
| Engagement | Post Likes + Comments | 1,000 | RM 0.20 | RM 200 |
| Brand Awareness | Video Views (3-second) | 10,000 | RM 0.05 | RM 500 |
| Total Campaign | — | — | — | RM 1,700 |

Note: RM 1,700 covers an 8-week paid media window. Full 90-day campaign budget is RM 3,115 (includes creative, tools, and additional lead gen spend — see Strategic Plan TVET-CU1-SMM-003).

## 4. Targeting Strategy

| Targeting Dimension | Parameter |
| --- | --- |
| Primary placement | Facebook News Feed (Mobile) — 65% of spend |
| Secondary placement | Instagram Reels + Feed — 35% of spend |
| Geography | Malaysia — Pahang (primary), Kelantan, Terengganu, Perak (secondary) |
| Age | 25–44 years (35–44 primary; 25–34 secondary) |
| Gender | Female (primary); Male (secondary — parents of graduates) |
| Interests | "Higher Education", "Vocational Training", "Parenting", "Early Childhood Education" |
| Behaviours | Parents with children aged 13–18; engaged with TVET/education pages |
| Retargeting | Custom Audience: Website visitors + video viewers (70%+ completion) |
| Lookalike | 1% Lookalike from existing Lead Form converters |

## 5. A/B Testing Plan

Management decision: Run creative A/B test in Week 1–2 to identify top performer before scaling spend:

| Test Variable | Variant A (Control) | Variant B (Challenger) | Decision Criteria |
| --- | --- | --- | --- |
| Ad Format | "PAKK Copywriting Lama" (proven) | New 30-sec Reel (student testimonial) | Higher CTR + lower CPL at Day 7 |
| Headline | "Anak Anda Boleh Dapat DKM" | "Belajar PERCUMA dengan PTPK" | Higher click-through rate |
| CTA Button | "Learn More" | "Sign Up" | Higher lead form completion |
| Audience | Interest-based broad | Lookalike 1% from existing leads | Lower CPL at Day 14 |

## 6. Optimization Schedule

| Week | Optimization Action | Decision Authority |
| --- | --- | --- |
| Week 1 | Launch all variants; monitor CTR and CPM daily | Zuriel |
| Week 2 | Pause underperforming variants (CTR < 1.0%) | Zuriel |
| Week 3–4 | Scale winning variant; add lookalike audiences | Zuriel (inform Lee Bee Chuan) |
| Week 5–6 | Introduce retargeting campaigns to warm audience | Zuriel |
| Week 7–8 | Final push: urgency creatives "Limited Seats"; increase budget | Lee Bee Chuan approval required |
| Post-camp | 90-day performance report to management | Zuriel → Lee Bee Chuan |

## 7. Management Focus — Budget Approval Summary

| Phase | Budget | Duration | Approval Required |
| --- | --- | --- | --- |
| Phase 1 — Testing | RM 400 | Week 1–2 | Pre-approved (Zuriel discretion ≤ RM 500) |
| Phase 2 — Scaling | RM 800 | Week 3–6 | Lee Bee Chuan sign-off required |
| Phase 3 — Final Push | RM 500 | Week 7–8 | Lee Bee Chuan sign-off required |
| Total | RM 1,700 | 8 weeks |  |

| Task | Responsible | Frequency |
| --- | --- | --- |
| Daily spend monitoring | Zuriel Seong Ming Ee | Daily |
| Weekly performance report | Zuriel → Lee Bee Chuan | Weekly |
| Budget phase approval (Phase 2 & 3) | Lee Bee Chuan | Week 2 + Week 6 |
| Creative production (new assets) | Zuriel + Designer | Bi-weekly |
| A/B test outcome decision | Zuriel (brief to mgmt) | Week 2 |

## Approval Section

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Zuriel Seong Ming Ee — Head of Sales & Digital Marketing | ___________________ | ___________ |
| Reviewed by | [PPT Supervisor / Assessor — Pending] | ___________________ | ___________ |
| Approved by | Lee Bee Chuan Managing Director, Fokus Kiara Sdn Bhd | ___________________ | ___________ |