# CU3 — Search Engine Marketing (SEM)
Budget Allocation & Bidding Strategy

Ref: TVET-CU3-SEM-002

Organisation: TVET Lipis (tvetlipis.my) — Fokus Kiara Sdn Bhd

Prepared by: Zuriel Seong Ming Ee — Head of Sales & Digital Marketing

Budget Period: April – June 2025 (3-month pilot)

Work Activities Covered: WA3 (Plan SEM Budget), WA4 (Implement SEM)

## 1. Strategic Purpose

This document details the RM 900 three-month Google Ads budget allocation for TVET Lipis's first SEM pilot campaign. Budget is distributed across ad groups based on keyword intent hierarchy, with a conservative Manual CPC bidding strategy transitioning to Smart Bidding after 30 days of conversion data. The plan includes daily caps, ad group splits, and a weekly optimisation schedule.

## 2. Total Budget Summary

| Month | Total Budget | Daily Cap | Expected Clicks | Expected Leads |
| --- | --- | --- | --- | --- |
| April 2025 | RM 300 | RM 10/day | 250–400 | 10–15 |
| May 2025 | RM 300 | RM 10/day | 250–400 | 10–15 |
| June 2025 | RM 300 | RM 10/day | 250–400 | 12–18 |
| Total / Avg | RM 900 | RM 10/day | 750–1,200 | 32–48 |

Assumptions: Avg CPC RM 0.75, CTR 5%, Conversion rate 4%. All figures are estimates pending live campaign data.

## 3. Ad Group Budget Distribution

| Ad Group | Monthly Budget | % of Total | Max CPC | Rationale |
| --- | --- | --- | --- | --- |
| Program — PAKK | RM 90 | 30% | RM 1.50 | Highest enrollment demand — primary program |
| Program — Multimedia | RM 60 | 20% | RM 1.20 | Strong youth market appeal |
| Program — Elektrik | RM 60 | 20% | RM 1.80 | High-intent trade seekers |
| PPT / DKM | RM 45 | 15% | RM 1.00 | Niche high-value audience |
| Brand | RM 30 | 10% | RM 0.50 | Brand protection — low CPC |
| Location / Generic | RM 15 | 5% | RM 0.70 | Discovery traffic support |
| TOTAL | RM 300 | 100% | -- | -- |

## 4. Bidding Strategy

| Phase | Duration | Bidding Strategy | Reason |
| --- | --- | --- | --- |
| Phase 1 — Learning | Week 1–2 | Manual CPC (conservative) | Establish baseline data safely |
| Phase 2 — Optimising | Week 3–6 | Enhanced CPC (eCPC) | Allow Google micro-adjustments within cap |
| Phase 3 — Smart | Week 7+ | Target CPA (if ≥30 conversions) | Automated bidding towards lead cost target |
| Fallback | If CPA insufficient | Return to Manual CPC | Prevent budget overrun on poor performers |

## 5. Weekly Optimisation Schedule

| Week | Action | Tool Used |
| --- | --- | --- |
| Week 1 | Launch campaign, monitor CTR and impressions | Google Ads Dashboard |
| Week 2 | Add negative keywords from search term report | Search Terms Report |
| Week 3 | A/B test ad headlines; pause low-CTR ads | Ad Performance Report |
| Week 4 | Review Quality Score; update landing page if QS < 6 | Keywords Report |
| Monthly | Full budget review; reallocate to best-performing ad groups | Monthly Report |

## 6. KPIs & Success Metrics

| KPI | Target (Month 1) | Target (Month 3) | Measurement |
| --- | --- | --- | --- |
| Click-Through Rate (CTR) | 4%+ | 6%+ | Google Ads |
| Cost Per Click (CPC) | < RM 1.20 | < RM 0.90 | Google Ads |
| Conversion Rate | 3%+ | 5%+ | Google Ads Conversions |
| Cost Per Lead (CPL) | < RM 40 | < RM 25 | Conversions ÷ Spend |
| Quality Score | 6/10+ | 7/10+ | Google Ads Keywords tab |
| Impressions | 5,000+ | 8,000+ | Google Ads |
| Leads Generated | 10+ | 15+ | CRM / WhatsApp log |

## 7. Management Focus — Task Delegation

| Task | Responsible | Frequency |
| --- | --- | --- |
| Campaign setup & go-live | Zuriel Seong Ming Ee | One-time (Apr 2025) |
| Daily budget monitoring | Zuriel | Daily |
| Weekly optimisation report | Zuriel → Lee Bee Chuan | Weekly |
| Ad copy refresh | Zuriel | Monthly |
| Monthly performance report | Zuriel (report to management) | Monthly |
| Budget reallocation decisions | Lee Bee Chuan (approval required) | Monthly |

## Approval Section

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | Zuriel Seong Ming Ee | ___________________ | ___________ |
| Reviewed by | [PPT Supervisor / Assessor — Pending] | ___________________ | ___________ |
| Approved by | Lee Bee Chuan Managing Director Fokus Kiara Sdn Bhd | ___________________ | ___________ |